## Sheet1
Story # | User story | task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
8 | As Scott Harris an anthropology professor, I want to make my own custom citation format, so that I can list the details I think are more important. [Priority: 10] (15 dh) | Design UI for making new citation format | Day 1: 7
|  | Integrate the new format into the app | Day 1: 5
|  | Write test plans | Day 1: 3
7 | As Scott Harris an anthropology professor, I want to be able to change the properties of multiple items at once, so I don’t have to do it one at a time. [Priority: 9] (21 dh) | Change the UI for property sidebar so it works when multiple items selected | Day 1: 8
|  | Pop the sidebar with property value in common and being able to change&save them | Day 1: 10
|  | Write test plans | Day 1: 3
6 | As Scott Harris an anthropology professor, I want to be able to ‘link’ two copies of the same item together, so that any changes affect both items at once. [Priority: 8] (30 dh) | Talk to customers to figure out what "copy" actually means | Day 1: 2
|  | Work out a way of efficiently linking items | Day 1: 15
|  | Recognize duplicated items and link them together | Day 1: 5
|  | Synchronize change made from one copy to another | Day 1: 5
|  | Write test plans | Day 1: 3
4 | As John Smith a history professor I want to search for similar tags so that I can check for typos. [Priority: 7] (50 dh) | Implement an algorithm to look for "similar" tags | Day 1: 30
96