## Sheet1
Story # | User story | task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
8 | As Scott Harris, an anthropology professor, I want to make my own custom citation format, so that I can list the details I think are more important. [Priority: 10] (15 dh) | Design UI for making new citation format (Cost:7dh) | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Integrate the new format into the app (Cost: 5dh) | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Write test plans (Cost: 3dh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | As Scott Harris, an anthropology professor, I want to be able to change the properties of multiple items at once, so that I don’t have to do it one at a time. [Priority: 9] (21 dh) | Change the UI for property sidebar so it works when multiple items selected (Cost:8dh) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Display the sidebar with property value in common and being able to change & save them (Cost:10dh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5
|  | Write test plans (Cost:3dh) | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | As Scott Harris, an anthropology professor, I want to be able to ‘link’ two copies of the same item together, so that any changes affect both items at once. [Priority: 8] (30 dh) | Talk to customers to figure out what "copy" actually means (Cost:2dh) | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Work out a way to efficiently link items (Cost:15dh) | 0 | 0 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0
|  | Recognize duplicated items and link them together(Cost:5dh) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 5
|  | Synchronize changes made from one copy to another(Cost::5dh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1
|  | Write test plans(Cost:3dh) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As John Smith a history professor I want to search for similar tags so that I can check for typos. [Priority: 7] (30 dh) | Implement an algorithm to look for "similar" tags(Cost:30) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1
Elliot(1)
Wei Cong(1)
XuFeng(1)
Raunak(1)
Owen(1)
6