## Sheet1
Sprint Backlog
Userstory # | User Story | Task
|  |  | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
1 | As Edward, a psychology student, I want to be able to add custom fields to my Zotero items, so that I can input information I think is important. [Priority: 10] (30 dh) | Create back end that talks to UI for adding fields to Zotero item | A:1 | 0 | A:2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create UI option to add fields to a zotero item. | 0 | 0 | 0 | A:1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | A:1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1+ | As Edward, a psychology student, I want the option to output my custom fields when I make my citations, so that I can properly show important information in my citations. [Priority: 10] (50 dh) | Create default citation format custom forms. | 0 | 0 | 0 | 0 | 0 | 0 | A:1 | 0 | A:2 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A:1 | 0 | A:1 | 0 | 0 | A:1 | 0
1++ | As Edward, a psychology student, I want to be able to remove fields from my Zotero items, so that I can remove information I think is not important. [Priority: 10] (30 dh) | Create UI option to remove existing fields from a Zotero item | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A:3 | 0 | 0 | 0
|  | Create back ends that talks to the UI for removing fields from a Zotero item. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1+++ | As Edward, a psychology student, I want to be able to save my zotero items with edited fields so that I can use them again later. [Priority: 10] (30 dh) | Create a save button for saving custom forms. | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | saves custom form to local file. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As Scott Harris, an anthropology professor, I want to have a context menu option to make a linked copy of the current item to another library so that I can easily make linked copies. [Priority: 9] (10 dh) | [2.1] Figure out how to modify item context menu that pops up on right click. | 0 | 0 | X:1 | X:1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | [2.1] Add context menu option to make a linked copy of the selected item(s). | 0 | 0 | 0 | X:1 | X:1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2+ | As Scott Harris, an anthropology professor, I want linked copies of the same item in different libraries to be synced so that changing one automatically changes others. | [2.2] Add functionality to auto update linked copies when the item they link to is changed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | X:1 | 0 | 0 | 0 | 0 | 0 | 0
|  | [2.2] Implement functionality so that indirectly linked copies will also be updated. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | X:2 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | X:1 | 0 | 0 | 0 | 0
2++ | As Scott Harris, an anthropology professor, I want to be able to choose the destination library and collection when I make a linked copy so that I don't have to manually move them around after the copy is created. [Priority: 5] (20 dh) | [2.3] Figure out how to show pop-up dialogues. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | X:2 | 0
|  | [2.3] Make a pop-up dialogue that prompts the user to choose a destination library and collection. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | X:2 | 0
|  | [2.3] Make the pop-up dialogue to auto update corresponding collections after the user chooses the destination library. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | X:1
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2+++ | As Scott Harris, an anthropology professor, I want to be able to choose the destination library and collection when I make a linked copy so that I don't have to manually move them around after the copy is created. [Priority: 5] (20 dh) | [2.4] Add functionality to detect possible cross-library duplications. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | [2.4] Prompt users for linking cross-library duplications detected. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | As John Smith, a history professor, I want to be able to see the tags of multiple items when I select them, so I can compare them to each other. [Priority: 8] (30 dh) | Add an 'Edit Tags' option in the tag search area (bottom left corner). | 0 | 0 | O:1 | 0 | 0 | O:1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Allow the search and multi-selection of tags for batch editing. | 0 | 0 | 0 | 0 | 0 | 0 | O:1 | 0 | O:1 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O:1 | 0 | 0 | 0 | 0
3+ | As John Smith, a history professor, I want to be able to edit all the tags of multiple selected items at once, so I don't have to do it one at a time. [Priority: 8] (50 dh) | Create UI for Tags when have multiple items selected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O:3 | 0 | 0
|  | Detection and indication of same value for tags. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O:1 | 0
|  | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3++ | As John Smith, a history professor, I want to be able to batch edit information and tags of multiple files, so that I don't have to do them one at a time. [Priority: 8] (50 dh) | Populate the Information & Tags field with corresponding item data when selected multiple items. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | E:1 | 0 | 0 | O:3
|  | Store user's update of tags back to database. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | R:1 | 0 | 0 | 0
|  | Functionionality to merge tags (from different names into one) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | R:2 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As Maunak Rathur, a student, I want to be able to reorder my citation fields when creating a citation, so that I can list the information that I think are more important. [Priority: 7] (45 dh) | [4] Code the UI so it displays retrieved fields & the number of fields. | 0 | 0 | E:2 | R:1 | R:2 | 0 | E:2 | 0 | E:2 | 0 | 0 | E:1 | 0 | 0
|  | [4] Code the retrieval of item fields for use in custom citations. | 0 | 0 | 0 | 0 | 0 | R:1 | R:1 | 0 | 0 | R:1 | 0 | 0 | 0 | 0
|  | [4] Give option for creation of custom citation when creating a bibliography. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | E:2 | 0 | 0 | R:2
4+ | As Maunak Rathur, a student, I want to be able to add or remove fields and punctuations when creating a citation, so that I can customize my citations. [Priority: 7] (25 dh) | [4] Allow outputting of custom citation style by parsing the user-created format. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | E:3
|  | [4] Create base UI for custom citation output. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4++ | As Maunak Rathur, a student, I want to be able to save my custom citation formats, so that I can use them again later. [Priority: 7] (30 dh) | [4] Allow saving of custom citation style. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | [4] Store saved citation into bibliography style list. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Acceptance Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| O for Owen | E for Elliot
| A for Alex | R for Raunak
X for Xufeng